# SALT and AMT Policy Calculator

Laura and John Arnold Foundation

Question: Provide a status update on the Milestones contained in the agreement, including: Milestone Description, Completion Date (per agreement), Status (complete/partial/N/A), and Explanation of Status.

Response:

## Milestone Status Update - Grant 24-11708

| # | Description | Due | Status | Explanation |
| --- | --- | --- | --- | --- |
| 1 | Quarterly check-in calls with AV Public Finance staff | Throughout | Complete | Held meetings Sept 2024 and Jan 2025. |
| 2 | Model enhancement: TAXSIM validation, property tax imputation, microdata forecasts, technical memo | Oct 15, 2024 | Partial | Built TAXSIM emulator with dashboard for validation. Property tax and microdata work not completed under this grant. |
| 3 | Launch SALT/AMT calculator integrated into PolicyEngine | Dec 1, 2024 | Delayed - Complete | Completed Apr 21, 2025. Launched SALTernative. Delay from refining “effective SALT cap” concept and income variation analysis beyond initial scope. |
| 4 | Technical report on SALT/AMT interactions and behavioral responses | Jan 15, 2025 | Delayed - Complete | Completed May 2025. Published H.R.1 analysis. Additional time needed for comprehensive analysis. |
| 5 | Grant Report | Feb 15, 2025 | Complete | This document. |

### Summary

All core deliverables completed. SALTernative launched April 21, 2025, shortly before the April 24, 2025 congressional webinar with Arnold Ventures. PolicyEngine’s H.R.1 analysis informed the OBBBA debate. Arnold Ventures published “Interactions Between the SALT Deduction and AMT Exemption” (May 2025) using PolicyEngine’s analysis.